## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
PB1 | Flight Search |  | As a user, I want to search flights by source, destination, and date | MUST HAVE | Flight database schema | Backend Team | 3- Completed
PB2 | Flight Data |  | As a system, I want to store flight, airline, and airport data | MUST HAVE | None | Backend Team | 3- Completed
PB3 | Dynamic Pricing |  | As a user, I want to see prices change based on demand and availability | MUST HAVE | Flight search API | Backend Team | 3- Completed
PB4 | Booking |  | As a user, I want to book a seat on a flight | MUST HAVE | Dynamic pricing engine | Backend Team | 3- Completed
PB5 | Concurrency |  | As a system, I want to prevent double booking of seats | MUST HAVE | Booking workflow | Backend Team | 2- In Progress
PB6 | Cancellation |  | As a user, I want to cancel my booking | SHOULD HAVE | Booking workflow | Backend Team | 2- In Progress
PB7 | Frontend UI |  | As a user, I want a simple UI to search and book flights | SHOULD HAVE | Backend APIs | Frontend Team | 3- Completed
PB8 | Receipts |  | As a user, I want to download booking receipts | COULD HAVE | Booking confirmation | Frontend Team | 2- In Progress
Note on F1: Mention the US ID(s) on which the user story depends. -Sumeet Kumar Barua08

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-01-07 | 14-07-2025 | Backend Developer | Start documenting DB schema decisions | Stop last-minute schema changes | Continue daily code reviews | Created finalized database ER diagram and shared with team
2 | Sprint 1 | 2025-01-07 | 14-07-2025 | Frontend Developer | Start early UI wireframing | Stop waiting for full backend completion | Continue requirement discussions | Prepared UI mockups in advance for integration
3 | Sprint 2 | 15-07-2025 | 28-07-2025 | Backend Developer | Start modular pricing logic | Stop hardcoding pricing values | Continue incremental testing | Refactored pricing engine into reusable functions
4 | Sprint 2 | 15-07-2025 | 28-07-2025 | Backend Developer | Start logging price changes | Stop ignoring edge cases | Continue demand simulation | Added logging for price fluctuations
5 | Sprint 3 | 29-07-2025 | 2025-11-08 | Backend Developer | Start transaction-based booking | Stop testing without concurrency | Continue API validation | Implemented database transactions and seat locking
6 | Sprint 3 | 29-07-2025 | 2025-11-08 | Backend Developer | Start UUID-based PNR generation | Stop sequential PNR creation | Continue booking workflow testing | Integrated UUID for unique PNRs
7 | Sprint 4 | 2025-12-08 | 25-08-2025 | Frontend Developer | Start UI performance optimization | Stop overloading single API calls | Continue frontend-backend sync | Optimized API calls and added loaders
8 | Sprint 4 | 2025-12-08 | 25-08-2025 | QA / Tester | Start end-to-end testing | Stop late bug reporting | Continue regression testing | Fixed UI and booking flow issues before final delivery

## sprint_backlog
Sprint ID | Task ID | User Story Ref | Task Description | Assignee | Est. Hours | Status
Sprint-1 | T-01 | US-01 | Setup Python Flask Backend structure and virtual environment | Chandra Mohan RS | 2 | Completed
Sprint-1 | T-02 | US-01 | Create 'flights.json' dummy database with mock flight data | Chandra Mohan RS | 1 | Completed
Sprint-1 | T-03 | US-01 | Develop GET /api/flights endpoint for search functionality | Chandra Mohan RS | 3 | Completed
Sprint-1 | T-04 | US-01 | Design Search HTML/CSS page with glassmorphism UI | Chandra Mohan RS | 4 | Completed
Sprint-1 | T-05 | US-03 | Create Booking API (POST /api/book) to generate PNR | Chandra Mohan RS | 3 | Completed
Sprint-1 | T-06 | US-04 | Implement Payment Gateway Mockup (payments.html) | Chandra Mohan RS | 3 | Completed
Sprint-1 | T-07 | US-05 | Integrate html2pdf.js library for ticket generation | Chandra Mohan RS | 4 | Completed
Sprint-1 | T-08 | US-06 | Fix CORS issues for Render Deployment (Localhost vs Live URL) | Chandra Mohan RS | 2 | Completed
Sprint-1 | T-09 | US-06 | Create 'My Bookings' page and fetch data from live API | Chandra Mohan RS | 3 | Completed

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Initial database schema confusion | Reviewed project requirements and finalized schema design
Sprint 1 | Day 2 | None | Continued API development as planned
Sprint 1 | Day 3 | Data validation issues | Added input validation and error handling
Sprint 2 | Day 9 | Complexity in pricing rules | Simplified pricing logic into modular functions
Sprint 2 | Day 12 | Demand simulation inconsistency | Adjusted demand simulation parameters
Sprint 3 | Day 18 | Concurrency handling uncertainty | Used database transactions and locking mechanism
Sprint 3 | Day 26 | PNR generation conflicts | Implemented UUID-based PNR generation
Sprint 4 | Day 28 | API response delay in UI | Optimized API calls and added loading states
Sprint 4 | Day 34 | Minor UI bugs | Fixed CSS and JavaScript validation issues